## Sheet1
Release 0.3.0: Connect Frontend Billing components to Backend
Ensure that the frontend can successfully retrieve and display data from the backend services
1. Billing info should populate from admin service data where applicable
Action: Convert studentContext.js to studentSlice.js
Action: Create billingSlice.js
2. Create applicable Stripe objects in backend like price and product.
Action: map existing users in Admin service to Stripe Customer objects
3. Teachers Can Create Customer
requirements:
If no Stripe Customer entity exists for user, render a button to sign user up.
Component with form to sign user up for a billing Subscription (create Subscription)
Link existing ManageBilling Component to relevant dispatches
5. Teachers can get billing history for students
6. teachers can edit Subscriptions for students
7. Teachers can delete subscriptions
If no Stripe Customer entity exists for user, render a button to sign user up.
Component with form to sign user up for a billing Subscription (create Subscription)
Link existing ManageBilling Component to relevant dispatches

## New Components
CreateStripeCustomer | Status
Component should fetch user by system id (useParams to get id in url) if state is empty | done
Component Should give feedback when customer is created | done
component should redirect back to student | done
Redux State should reset
Form Validation - disable submit button if formstate not complete
handle loading state
Create Subscription
Component should fetch Stripe customer (useParams to get id in url) if state is empty | done
Component Should give feedback when subscription is created
component should redirect back to student on success
Redux State should reset
Form Validation - disable submit button if formstate not complete
handle loading state
Create Payment Method
Component should give feedback when payment method is created / confirmed | done
CreateSubscription component should fetch and render new payment methods in form when a new payment method is created
Redux State should reset
Standalone version of New{PaymentMethod
handle loading state
Billing Overview
Button should render correctly when new customer is created | done
handle loading state

## General
General Issues/Enhancements | Comments
Refactor new components to use entity adapters instead of creating redundant state objects
Refactor remaining Redux reducers to use the entity namespaces
Remove poorly designed/unused backend classes
clearAll in billing when SingleStudent Component closes
Issue: payment method not attaching to customer on creation | resolution: conditional rendering caused paymentmethod modal to unmount on submit. Removed loadning state, but need to refactor use of loading state prop
Remaining Features:
Implement Invoices
Lesson Events should increment a Meter (Integrate event service)
Aattach Payment Methods to Subscriptions
Refactor to PaymentElement instead of CardElement for creating payment methods | future enhancement

## Final Release Features
Remaining Features: | Comments:
Setup Intents should get confirmed once created | clear unused setupintents manually
Subscriptions should genertate a monthly invoice | New API endpoints needed
Lesson Events should increment a Meter | Integrate event service
Aattach Payment Methods to Subscriptions | Finish frontend ManagePaymentMethod component
Finish ManageSubscription.jsx Billing History
Finish ManageSubscription.jsx Manage Susbscription type
Finish ManageSubscription.jsx Manage Payment Methods
Finish ManageSubscription.jsx Subscription Details
Use Case: User has no payment method set up
find pm for customer if one exists, otherwise create pm
update request using pm for that
Refactor to PaymentElement instead of CardElement for creating payment methods | future enhancement
Email/Message service should send a system message reminding teachers to log lessons before invoices are finalized | future enhancement

## Invoice Feature
Feature Objectives:
Subscriptions should genertate a monthly invoice
Lesson Events should increment a Meter
Steps to implement:
Create a workflow for marking lesson attendance
Render new component within: /src/pages/Teachers/Lessons.jsx | components: LessonList - show all lessons for teacher in the month
Within LessonList table - Render Button for 'Mark Attendance' (Only Enable if current date > lessonDate)
when a lesson event is logged, dispatch API Call to create a corresponding MeterEvent object